{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Lot Date Analysis","Data"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Lot Date Analysis","index":0,"n_rows":3,"n_cols":7,"rows_kept":3,"cut":false,"hidden":false,"merged":[]}
["Finishing Schedule",null,null,null,null,null,"Report Date:"]
[]
["Construction Priority","Lot #","Closing Date"]

{"sheet":"Data","index":1,"n_rows":451,"n_cols":7,"rows_kept":451,"cut":false,"hidden":false,"merged":[]}
["Lot Count",58]
["Key Date Count",10]
["Lot Key Date Count",372]
["Lateness Threshold",7]
["Report Date","2025-01-15"]
[]
["Lot Priority","Lot Code","Closing Date"]
[0,"PHASE MR1-1-00-00"]
[0,"TOWNHOUSE-1-00-00T"]
[0,"PHASE MR1-1-01-00"]
[0,"PHASE MR1-1-01-01"]
[0,"TOWNHOUSE-1-01-01T"]
[0,"PHASE MR1-1-01-02"]
[0,"PHASE MR1-1-02-01"]
[0,"PHASE MR1-1-02-02"]
[0,"PHASE MR1-1-02-03"]
[0,"PHASE MR1-1-02-04"]
[0,"PHASE MR1-1-03-00"]
[0,"PHASE MR1-1-03-01"]
[0,"PHASE MR1-1-03-02"]
[0,"PHASE MR1-1-03-03"]
[0,"PHASE 1-LOT0001","2025-02-05"]
[0,"PHASE 1-LOT0002","2024-04-30"]
[0,"PHASE 1-LOT0003","2024-04-17"]
[0,"PHASE 1-LOT0004"]
[0,"PHASE 1-LOT0005",null,"Bold","Uppercase","Font Color","Backgroup Color"]
[0,"PHASE 1-LOT0042",null,"No","No","Black","White"]
[0,"PHASE 1-LOT0043",null,"Yes","No","White","Black"]
[0,"PHASE 1-LOT0044",null,"No","No","Black","Yellow"]
[0,"PHASE 1-LOT0045",null,"No","No","Black","Yellow"]
[0,"PHASE 1-LOT0046",null,"Bold","Uppercase","Font Color","Backgroup Color"]
[0,"PHASE 1-LOT0047",null,"No","No","Black","White"]
[0,"PHASE MR1-M0-00-00",null,"No","No","Black","White"]
[0,"PHASE MR1-M1-02-00",null,"No","No","Black","White"]
[0,"PHASE MR1-M1-03-04",null,"No","No","Black","White"]
[0,"PHASE MR1-M2-00-00",null,"No","No","Black","White"]
[0,"TOWNHOUSE-T0-00-00",null,"No","No","Black","White"]
[1,"PHASE 1-LOT0006",null,"No","No","Black","White"]
[1,"PHASE 1-LOT0007",null,"No","No","Black","White"]
[1,"PHASE 1-LOT0008",null,"No","No","Black","White"]
[2,"PHASE 1-LOT0009",null,"No","No","Black","White"]
[2,"PHASE 1-LOT0010",null,"No","No","Black","White"]
[2,"PHASE 1-LOT0011",null,"No","No","Black","White"]
[2,"PHASE 1-LOT0012",null,"Actual Date","Backgroup Color","Black","White"]
[2,"PHASE 1-LOT0013",null,null,"White"]
[2,"PHASE 1-LOT0014",null,"2023-01-24","Yellow"]
[2,"PHASE 1-LOT0015",null,"2023-02-01","Green"]
[2,"PHASE 1-LOT0016",null,"2023-01-12","Yellow"]
[2,"PHASE 1-LOT0017",null,"2022-11-16","Red"]
[2,"PHASE 1-LOT0018",null,"2022-12-20","Yellow"]
[2,"PHASE 1-LOT0019",null,"2022-11-23","Green"]
[2,"PHASE 1-LOT0020",null,"2022-11-28","Green"]
[2,"PHASE 1-LOT0021",null,null,"White"]
[2,"PHASE 1-LOT0022",null,null,"White"]
[2,"PHASE 1-LOT0023",null,"2023-01-03","Green"]
[2,"PHASE 1-LOT0024",null,null,"Red"]
[2,"PHASE 1-LOT0025",null,null,"Red"]
[2,"PHASE 1-LOT0026",null,null,"Red"]
[2,"PHASE 1-LOT0028",null,null,"Red"]
[2,"PHASE 1-LOT0029","2024-04-30","2022-08-24","Green"]
[2,"PHASE 1-LOT0032","2025-02-04","2023-07-19","Green"]
[2,"PHASE 1-LOT0033","2025-01-30","2023-01-24","Green"]
[2,"PHASE 1-LOT0040",null,"2023-01-24","Green"]
[2,"PHASE 1-LOT0041",null,null,"Red"]
[2,"PHASE 1-OVERHEAD L",null,null,"Red"]
["SV1-L002","WINDOWS","2023-07-26","2023-07-26","Green"]
["Key Date Code","Key Date Name","Font Size","Bold","Uppercase","Font Color","Backgroup Color"]
["FOOT INSP","Municipal Footing And Foundation Inspection","8","No","No","Black","White"]
["FRAM SUB 1","Framing First Sub Floor","8","No","No","Black","White"]
["FRAM SUB 2","Framing Second Sub Floor","8","No","No","Black","White"]
["FRAM INSP","Framing Inspection ","8","No","No","Black","White"]
["ELEC INSP","Electrical Inspection ","8","No","No","Black","White"]
["DRYWALLING","Drywalling (All Tasks)","8","No","No","Black","White"]
["WINDOWS","Windows And Doors Installation","8","No","No","Black","White"]
["QC INSPECT","Quality Control Inspection ","8","No","No","Black","White"]
["PDI","PDI Inspection","8","No","No","Black","White"]
["CLS FINAL","Final Closing","8","No","No","Black","White"]
["SV1-L004","CLS FINAL","2023-12-01",null,"Red"]
["Lot Code","Key Date Code","Scheduled Date","Actual Date","Backgroup Color"]
["PHASE 1-LOT0001","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0001","DRYWALLING","2024-11-20",null,"Red"]
["PHASE 1-LOT0001","ELEC INSP","2024-10-01",null,"Red"]
["PHASE 1-LOT0001","FOOT INSP","2024-07-19",null,"Red"]
["PHASE 1-LOT0001","FRAM INSP","2024-09-11",null,"Red"]
["PHASE 1-LOT0001","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0001","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0001","PDI","2024-12-19",null,"Red"]
["PHASE 1-LOT0001","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0001","WINDOWS",null,null,"White"]
["PHASE 1-LOT0002","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0002","DRYWALLING",null,"2025-01-06","White"]
["PHASE 1-LOT0002","ELEC INSP","2025-01-17",null,"White"]
["PHASE 1-LOT0002","FOOT INSP","2025-01-29",null,"White"]
["PHASE 1-LOT0002","FRAM INSP","2025-01-14",null,"Yellow"]
["PHASE 1-LOT0002","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0002","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0002","PDI",null,"2024-12-18","White"]
["PHASE 1-LOT0002","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0002","WINDOWS",null,null,"White"]
["PHASE 1-LOT0003","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0003","DRYWALLING","2025-08-01",null,"White"]
["PHASE 1-LOT0003","ELEC INSP","2025-05-28",null,"White"]
["PHASE 1-LOT0003","FOOT INSP","2025-02-03",null,"White"]
["PHASE 1-LOT0003","FRAM INSP","2025-05-05",null,"White"]
["PHASE 1-LOT0003","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0003","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0003","PDI","2025-09-16",null,"White"]
["PHASE 1-LOT0003","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0003","WINDOWS",null,null,"White"]
["PHASE 1-LOT0004","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0004","DRYWALLING","2025-06-03",null,"White"]
["PHASE 1-LOT0004","ELEC INSP","2025-03-31",null,"White"]
["PHASE 1-LOT0004","FOOT INSP","2024-11-22",null,"Red"]
["PHASE 1-LOT0004","FRAM INSP","2025-03-06",null,"White"]
["PHASE 1-LOT0004","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0004","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0004","PDI","2025-07-18",null,"White"]
["PHASE 1-LOT0004","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0004","WINDOWS",null,null,"White"]
["PHASE 1-LOT0005","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0005","DRYWALLING","2024-09-17",null,"Red"]
["PHASE 1-LOT0005","ELEC INSP","2024-07-29",null,"Red"]
["PHASE 1-LOT0005","FOOT INSP","2024-05-06",null,"Red"]
["PHASE 1-LOT0005","FRAM INSP","2024-07-09",null,"Red"]
["PHASE 1-LOT0005","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0005","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0005","PDI","2024-10-16",null,"Red"]
["PHASE 1-LOT0005","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0005","WINDOWS",null,null,"White"]
["PHASE 1-LOT0006","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0006","DRYWALLING","2024-09-13",null,"Red"]
["PHASE 1-LOT0006","ELEC INSP","2024-07-25",null,"Red"]
["PHASE 1-LOT0006","FOOT INSP","2024-05-02",null,"Red"]
["PHASE 1-LOT0006","FRAM INSP","2024-07-05",null,"Red"]
["PHASE 1-LOT0006","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0006","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0006","PDI","2024-10-14",null,"Red"]
["PHASE 1-LOT0006","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0006","WINDOWS",null,null,"White"]
["PHASE 1-LOT0007","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0007","DRYWALLING","2024-09-17",null,"Red"]
["PHASE 1-LOT0007","ELEC INSP","2024-07-29",null,"Red"]
["PHASE 1-LOT0007","FOOT INSP","2024-05-06",null,"Red"]
["PHASE 1-LOT0007","FRAM INSP","2024-07-09",null,"Red"]
["PHASE 1-LOT0007","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0007","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0007","PDI","2024-10-16",null,"Red"]
["PHASE 1-LOT0007","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0007","WINDOWS",null,null,"White"]
["PHASE 1-LOT0008","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0008","DRYWALLING","2024-08-28",null,"Red"]
["PHASE 1-LOT0008","ELEC INSP","2024-07-09",null,"Red"]
["PHASE 1-LOT0008","FOOT INSP","2024-05-01",null,"Red"]
["PHASE 1-LOT0008","FRAM INSP","2024-06-18",null,"Red"]
["PHASE 1-LOT0008","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0008","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0008","PDI","2024-09-26",null,"Red"]
["PHASE 1-LOT0008","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0008","WINDOWS",null,null,"White"]
["PHASE 1-LOT0009","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0009","DRYWALLING","2024-09-19",null,"Red"]
["PHASE 1-LOT0009","ELEC INSP","2024-07-31",null,"Red"]
["PHASE 1-LOT0009","FOOT INSP","2024-05-08",null,"Red"]
["PHASE 1-LOT0009","FRAM INSP","2024-07-11",null,"Red"]
["PHASE 1-LOT0009","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0009","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0009","PDI","2024-10-18",null,"Red"]
["PHASE 1-LOT0009","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0009","WINDOWS",null,null,"White"]
["PHASE 1-LOT0010","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0010","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0010","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0010","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0010","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0010","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0010","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0010","PDI",null,null,"White"]
["PHASE 1-LOT0010","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0010","WINDOWS",null,null,"White"]
["PHASE 1-LOT0011","DRYWALLING","2024-11-06","2024-04-18","Green"]
["PHASE 1-LOT0011","ELEC INSP","2024-09-03","2024-04-18","Green"]
["PHASE 1-LOT0011","FOOT INSP","2024-05-09","2024-04-18","Green"]
["PHASE 1-LOT0011","FRAM INSP","2024-08-09","2024-04-18","Green"]
["PHASE 1-LOT0011","PDI","2024-12-20","2024-04-18","Green"]
["PHASE 1-LOT0012","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0012","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0012","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0012","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0012","PDI",null,null,"White"]
["PHASE 1-LOT0013","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0013","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0013","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0013","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0013","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0013","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0013","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0013","PDI",null,null,"White"]
["PHASE 1-LOT0013","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0013","WINDOWS",null,null,"White"]
["PHASE 1-LOT0014","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0014","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0014","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0014","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0014","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0014","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0014","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0014","PDI",null,null,"White"]
["PHASE 1-LOT0014","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0014","WINDOWS",null,null,"White"]
["PHASE 1-LOT0015","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0015","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0015","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0015","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0015","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0015","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0015","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0015","PDI",null,null,"White"]
["PHASE 1-LOT0015","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0015","WINDOWS",null,null,"White"]
["PHASE 1-LOT0016","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0016","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0016","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0016","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0016","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0016","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0016","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0016","PDI",null,null,"White"]
["PHASE 1-LOT0016","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0016","WINDOWS",null,null,"White"]
["PHASE 1-LOT0017","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0017","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0017","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0017","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0017","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0017","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0017","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0017","PDI",null,null,"White"]
["PHASE 1-LOT0017","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0017","WINDOWS",null,null,"White"]
["PHASE 1-LOT0018","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0018","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0018","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0018","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0018","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0018","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0018","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0018","PDI",null,null,"White"]
["PHASE 1-LOT0018","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0018","WINDOWS",null,null,"White"]
["PHASE 1-LOT0019","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0019","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0019","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0019","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0019","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0019","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0019","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0019","PDI",null,null,"White"]
["PHASE 1-LOT0019","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0019","WINDOWS",null,null,"White"]
["PHASE 1-LOT0020","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0020","DRYWALLING","2025-07-23",null,"White"]
["PHASE 1-LOT0020","ELEC INSP","2025-05-19",null,"White"]
["PHASE 1-LOT0020","FOOT INSP","2025-01-23",null,"White"]
["PHASE 1-LOT0020","FRAM INSP","2025-04-24",null,"White"]
["PHASE 1-LOT0020","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0020","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0020","PDI","2025-09-05",null,"White"]
["PHASE 1-LOT0020","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0020","WINDOWS",null,null,"White"]
["PHASE 1-LOT0021","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0021","DRYWALLING","2025-05-29",null,"White"]
["PHASE 1-LOT0021","ELEC INSP","2025-03-26",null,"White"]
["PHASE 1-LOT0021","FOOT INSP","2025-01-23",null,"White"]
["PHASE 1-LOT0021","FRAM INSP","2025-03-03",null,"White"]
["PHASE 1-LOT0021","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0021","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0021","PDI","2025-01-03",null,"Red"]
["PHASE 1-LOT0021","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0021","WINDOWS",null,null,"White"]
["PHASE 1-LOT0022","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0022","DRYWALLING","2025-07-23",null,"White"]
["PHASE 1-LOT0022","ELEC INSP","2025-05-19",null,"White"]
["PHASE 1-LOT0022","FOOT INSP","2025-01-23",null,"White"]
["PHASE 1-LOT0022","FRAM INSP","2025-04-24",null,"White"]
["PHASE 1-LOT0022","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0022","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0022","PDI","2025-09-05",null,"White"]
["PHASE 1-LOT0022","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0022","WINDOWS",null,null,"White"]
["PHASE 1-LOT0023","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0023","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0023","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0023","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0023","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0023","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0023","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0023","PDI",null,null,"White"]
["PHASE 1-LOT0023","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0023","WINDOWS",null,null,"White"]
["PHASE 1-LOT0024","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0024","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0024","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0024","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0024","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0024","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0024","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0024","PDI","2025-02-24",null,"White"]
["PHASE 1-LOT0024","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0024","WINDOWS",null,null,"White"]
["PHASE 1-LOT0025","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0025","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0025","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0025","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0025","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0025","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0025","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0025","PDI",null,null,"White"]
["PHASE 1-LOT0025","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0025","WINDOWS",null,null,"White"]
["PHASE 1-LOT0026","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0026","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0026","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0026","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0026","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0026","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0026","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0026","PDI",null,null,"White"]
["PHASE 1-LOT0026","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0026","WINDOWS",null,null,"White"]
["PHASE 1-LOT0028","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0028","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0028","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0028","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0028","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0028","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0028","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0028","PDI",null,null,"White"]
["PHASE 1-LOT0028","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0028","WINDOWS",null,null,"White"]
["PHASE 1-LOT0029","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0029","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0029","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0029","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0029","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0029","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0029","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0029","PDI",null,null,"White"]
["PHASE 1-LOT0029","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0029","WINDOWS",null,null,"White"]
["PHASE 1-LOT0032","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0032","DRYWALLING","2025-07-23",null,"White"]
["PHASE 1-LOT0032","ELEC INSP","2025-05-19",null,"White"]
["PHASE 1-LOT0032","FOOT INSP","2025-01-23",null,"White"]
["PHASE 1-LOT0032","FRAM INSP","2025-04-24",null,"White"]
["PHASE 1-LOT0032","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0032","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0032","PDI","2025-09-05",null,"White"]
["PHASE 1-LOT0032","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0032","WINDOWS",null,null,"White"]
["PHASE 1-LOT0033","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0033","DRYWALLING","2025-03-24",null,"White"]
["PHASE 1-LOT0033","ELEC INSP","2025-01-31",null,"White"]
["PHASE 1-LOT0033","FOOT INSP","2024-10-17",null,"Red"]
["PHASE 1-LOT0033","FRAM INSP","2025-01-13",null,"Yellow"]
["PHASE 1-LOT0033","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0033","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0033","PDI","2024-09-30",null,"Red"]
["PHASE 1-LOT0033","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0033","WINDOWS",null,null,"White"]
["PHASE 1-LOT0040","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0040","DRYWALLING","2025-05-21",null,"White"]
["PHASE 1-LOT0040","ELEC INSP","2025-04-01",null,"White"]
["PHASE 1-LOT0040","FOOT INSP","2025-01-17",null,"White"]
["PHASE 1-LOT0040","FRAM INSP","2025-03-12",null,"White"]
["PHASE 1-LOT0040","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0040","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0040","PDI","2025-06-19",null,"White"]
["PHASE 1-LOT0040","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0040","WINDOWS",null,null,"White"]
["PHASE 1-LOT0041","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0041","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0041","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0041","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0041","PDI",null,null,"White"]
["PHASE 1-LOT0042","DRYWALLING",null,null,"White"]
["PHASE 1-LOT0042","ELEC INSP",null,null,"White"]
["PHASE 1-LOT0042","FOOT INSP",null,null,"White"]
["PHASE 1-LOT0042","FRAM INSP",null,null,"White"]
["PHASE 1-LOT0042","PDI",null,null,"White"]
["PHASE 1-LOT0043","CLS FINAL",null,null,"White"]
["PHASE 1-LOT0043","DRYWALLING","2025-07-16",null,"White"]
["PHASE 1-LOT0043","ELEC INSP","2025-05-14",null,"White"]
["PHASE 1-LOT0043","FOOT INSP","2025-01-28",null,"White"]
["PHASE 1-LOT0043","FRAM INSP","2025-04-14",null,"White"]
["PHASE 1-LOT0043","FRAM SUB 1",null,null,"White"]
["PHASE 1-LOT0043","FRAM SUB 2",null,null,"White"]
["PHASE 1-LOT0043","PDI","2025-08-29",null,"White"]
["PHASE 1-LOT0043","QC INSPECT",null,null,"White"]
["PHASE 1-LOT0043","WINDOWS",null,null,"White"]
["PHASE 1-OVERHEAD L","CLS FINAL",null,null,"White"]
["PHASE 1-OVERHEAD L","DRYWALLING",null,null,"White"]
["PHASE 1-OVERHEAD L","ELEC INSP",null,null,"White"]
["PHASE 1-OVERHEAD L","FOOT INSP",null,null,"White"]
["PHASE 1-OVERHEAD L","FRAM INSP",null,null,"White"]
["PHASE 1-OVERHEAD L","FRAM SUB 1",null,null,"White"]
["PHASE 1-OVERHEAD L","FRAM SUB 2",null,null,"White"]
["PHASE 1-OVERHEAD L","QC INSPECT",null,null,"White"]
["PHASE 1-OVERHEAD L","WINDOWS",null,null,"White"]
["PHASE MR1-1-00-00","FOOT INSP",null,null,"White"]
["PHASE MR1-1-00-00","FRAM INSP",null,null,"White"]
["PHASE MR1-1-01-00","DRYWALLING","2025-03-12",null,"White"]
["PHASE MR1-1-01-00","ELEC INSP","2025-01-21",null,"White"]
["PHASE MR1-1-01-01","DRYWALLING","2025-01-23",null,"White"]
["PHASE MR1-1-01-01","ELEC INSP","2025-01-15",null,"White"]
["PHASE MR1-1-01-01","PDI","2025-03-18",null,"White"]
["PHASE MR1-1-01-02","DRYWALLING",null,null,"White"]
["PHASE MR1-1-01-02","ELEC INSP",null,null,"White"]
["PHASE MR1-1-01-02","PDI",null,null,"White"]
["PHASE MR1-1-02-01","DRYWALLING",null,null,"White"]
["PHASE MR1-1-02-01","ELEC INSP",null,null,"White"]
["PHASE MR1-1-02-01","PDI",null,null,"White"]
["PHASE MR1-1-02-02","DRYWALLING",null,null,"White"]
["PHASE MR1-1-02-02","ELEC INSP",null,null,"White"]
["PHASE MR1-1-02-02","PDI",null,null,"White"]
["PHASE MR1-1-02-03","DRYWALLING",null,null,"White"]
["PHASE MR1-1-02-03","ELEC INSP",null,null,"White"]
["PHASE MR1-1-02-03","PDI",null,null,"White"]
["PHASE MR1-1-02-04","DRYWALLING",null,null,"White"]
["PHASE MR1-1-02-04","ELEC INSP",null,null,"White"]
["PHASE MR1-1-02-04","PDI",null,null,"White"]
["PHASE MR1-1-03-00","DRYWALLING",null,null,"White"]
["PHASE MR1-1-03-00","ELEC INSP",null,null,"White"]
["PHASE MR1-1-03-01","DRYWALLING",null,null,"White"]
["PHASE MR1-1-03-01","ELEC INSP",null,null,"White"]
["PHASE MR1-1-03-01","PDI",null,null,"White"]
["PHASE MR1-1-03-02","DRYWALLING",null,null,"White"]
["PHASE MR1-1-03-02","ELEC INSP",null,null,"White"]
["PHASE MR1-1-03-02","PDI",null,null,"White"]
["PHASE MR1-1-03-03","DRYWALLING",null,null,"White"]
["PHASE MR1-1-03-03","ELEC INSP",null,null,"White"]
["PHASE MR1-1-03-03","PDI",null,null,"White"]
["PHASE MR1-M1-02-00","DRYWALLING",null,null,"White"]
["PHASE MR1-M1-02-00","ELEC INSP",null,null,"White"]
["PHASE MR1-M1-03-04","DRYWALLING",null,null,"White"]
["PHASE MR1-M1-03-04","ELEC INSP",null,null,"White"]
["PHASE MR1-M1-03-04","PDI",null,null,"White"]
["TOWNHOUSE-1-00-00T","FOOT INSP","2025-02-19",null,"White"]
["TOWNHOUSE-1-00-00T","FRAM INSP","2025-09-19",null,"White"]
["TOWNHOUSE-1-01-01T","DRYWALLING","2025-01-23",null,"White"]
["TOWNHOUSE-1-01-01T","ELEC INSP","2025-01-15",null,"White"]
["TOWNHOUSE-1-01-01T","PDI","2025-03-18",null,"White"]